## Dashboard
Analysis of data from Steam
Description: This is a document resource overview of the analysis of data from Steam project
Owner: Mahad Osman, Alex Hicks, Aseel Ibrahim
Status: Final
Key Docs | Description
Project charter | An overview of the project, key elements and expectations
Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially.
Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle.
Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Folder with all relevant documentation
RACI chart | Identifies who is responsible, accountable, consulted and informed within the project.
Note on A7: Add hyperlink to digital document, Project charter
Note on A8: Add hyperlink to digital document, Statement of work
Note on A9: Add hyperlink to digital document, risk management plan
Note on A13: Add hyperlink to a shared folder
Note on A14: Add hyperlink to RACI chart spreadsheet

## Project Schedule
Gantt Chart
TITLE: Analysis of data from Steam | [6 empty] | COMPANY NAME:
PROJECT MANAGER: Mahad Osman, Alex Hicks, Aseel Ibrahim | [6 empty] | CREATION DATE: |  |  |  |  | 12/11
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Gather data from Steam | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Research | Mahad Osman | 1/1 | 1/8 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Downloading the data | Mahad Osman | 1/10 | 1/18 | 20 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Formatting the data | Mahad Osman | 1/20 | 1/26 | 7 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Create a frontend for the user
2.1 | Research | Alex Hicks | 1/28 | 2/4 | 10 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Configuration | Mahad Osman | 2/10 | 2/19 | 15 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Implementing | Alex Hicks | 2/26 | 3/5 | 15 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Configure and manage the web app
3.1 | Research | Aseel Ibrahim | 3/10 | 3/19 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Configuring | Aseel Ibrahim | 3/26 | 4/2 | 20 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Implementing | Aseel Ibrahim | 4/8 | 4/15 | 15 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: Steam analysis project
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 0 | 0 | 0
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Task 1:Set up a host | Aseel Ibrahim | 44 |  | 0 | 0 |  | 0 |  | 0
Task 2: Gather Data from Steam | Mahad Osman | 45 |  | 0 | 0 |  | 0 |  | 0
Task 3: Create a user frontend | Alex Hicks | 43 | 0 |  |  |  | 0 |  | 0
TOTAL | [6 empty] | 0 | 0
0
0
0
0

## Communication Plan
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Notes
Team Meeting | General Meeting | Once a week | Project Manager | Every Monday | In Person | Continue to develop the project | Each week, will go over what we’ve worked on, what next, and any questions we have.
Jeff meeting | Planning Check-In | Once a week | Jeff Kinne | Every Friday | In Person | Explain and discuss the project with Mr. Kinne | Every week, we’ll meet with Mr. Kinne to discuss where we are in the project and what’s left for us.